AI Safety Guard

Chrome Extension

Implementation Plan

Based on PRD v1.0  •  June 2026

# Overview

This document provides a complete, step-by-step implementation plan for building the AI Safety Guard Chrome Extension — a free tool that warns users before pasting or submitting sensitive information into AI tools such as ChatGPT, Claude, Gemini, Perplexity, and Microsoft Copilot.

The plan is organized into 5 phases spanning approximately 8–10 weeks from setup to Chrome Web Store submission.

North Star Goal Prevent risky AI submissions. Every feature decision should be measured against this: does it help users avoid accidentally exposing sensitive data to AI tools?

## Tech Stack

- Manifest V3 Chrome Extension (required by Chrome Web Store)

- Vanilla JavaScript — no frameworks needed for content scripts

- HTML + CSS for popup, onboarding, and warning modal

- Node.js + Webpack (or Vite) for build tooling

- Chrome Storage API for persisting user settings

- Optional: external rewrite API (OpenAI-compatible) called only on user request

## Phase Summary

| Phase | Name | Duration | Goal |
| --- | --- | --- | --- |
| 1 | Project Setup | 3–4 days | Repo, manifest, build pipeline, CI |
| 2 | Detection Engine | 1–1.5 weeks | All regex/keyword/entropy detectors |
| 3 | Content Scripts & UI | 1.5–2 weeks | Risk badge, warning modal, redaction |
| 4 | Settings & Onboarding | 1 week | Popup UI, onboarding flow, storage |
| 5 | Polish & Ship | 1–1.5 weeks | Testing, privacy audit, CWS submission |

PHASE 1: Project Setup & Scaffolding Duration: 3–4 days • Skeleton extension that loads in Chrome

## 1.1  Create the Repository

- Create a new Git repo: ai-safety-guard

- Add a .gitignore for Node.js (node_modules, dist/, .env)

- Initialize with npm init and install dev dependencies:

  - webpack, webpack-cli, copy-webpack-plugin

  - eslint, prettier

  - web-ext (Mozilla's extension testing tool, works for Chrome too)

## 1.2  Directory Structure

| File / Directory | Purpose |
| --- | --- |
| ai-safety-guard/ | Root of the repo |
| manifest.json | Extension manifest (MV3) |
| src/ | All source code |
| src/background/ | Service worker |
| src/background/service-worker.js | Background entry point |
| src/content/ | Content scripts (injected into AI sites) |
| src/content/content.js | Main content script entry |
| src/content/detector.js | Detection engine (regex, entropy, keywords) |
| src/content/redactor.js | Auto-redaction logic |
| src/content/ui/badge.js | Inline risk badge component |
| src/content/ui/modal.js | Warning modal component |
| src/content/sites/ | Per-site DOM selectors |
| src/content/sites/chatgpt.js | ChatGPT input selectors |
| src/content/sites/claude.js | Claude.ai input selectors |
| src/content/sites/gemini.js | Gemini input selectors |
| src/content/sites/perplexity.js | Perplexity input selectors |
| src/content/sites/copilot.js | Microsoft Copilot selectors |
| src/popup/ | Extension popup (settings) |
| src/popup/popup.html | Popup HTML |
| src/popup/popup.js | Popup logic |
| src/popup/popup.css | Popup styles |
| src/onboarding/ | First-install onboarding page |
| src/onboarding/onboarding.html | Onboarding HTML |
| src/onboarding/onboarding.js | Onboarding logic |
| src/shared/ | Shared utilities |
| src/shared/constants.js | Risk levels, categories, site list |
| src/shared/storage.js | Chrome storage read/write helpers |
| src/shared/rules.json | Detection rules (regex + keywords) |
| assets/ | Icons, images |
| assets/icons/ | icon16.png, icon48.png, icon128.png |
| dist/ | Build output (git-ignored) |
| webpack.config.js | Webpack build config |

## 1.3  manifest.json

This is the heart of the extension. Key fields for Manifest V3:

- manifest_version: 3

- permissions: ["storage", "activeTab", "scripting"]

- host_permissions: list of all supported AI site URLs (e.g., https://chatgpt.com/*)

- background.service_worker: points to the compiled service worker

- content_scripts: inject content.js on all supported AI site URLs

- action: popup.html (the settings popup)

- icons: 16, 48, 128px PNGs

- options_page or chrome_url_overrides: not needed for MVP

Important: Manifest V3 Restriction MV3 service workers cannot use XMLHttpRequest or fetch in all contexts. Use the Offscreen API or messaging from content scripts for any network calls. All detection runs in content scripts — no background network access needed for local scanning.

## 1.4  Build Pipeline (Webpack)

- Entry points: background/service-worker.js, content/content.js, popup/popup.js

- Output: dist/ folder with all compiled JS

- Copy manifest.json, HTML files, and assets/icons to dist/ with CopyWebpackPlugin

- Add npm scripts: "build", "watch", "lint"

- Load unpacked extension in Chrome from the dist/ folder during development

## 1.5  Verify It Loads

- Go to chrome://extensions in Chrome

- Enable Developer Mode

- Click "Load unpacked" and select your dist/ folder

- Confirm the extension icon appears in the toolbar

- Open ChatGPT — no errors in the console yet means success

PHASE 2: Detection Engine Duration: 1–1.5 weeks • Accurate, fast, local-only scanning

The detection engine is the core of AI Safety Guard. It runs entirely in the browser — no data leaves the device during scanning. Build it in src/content/detector.js as a pure function that takes a string and returns a structured result.

## 2.1  Output Contract

The detector should return an object with this shape for every scan:

| Field | Type | Description |
| --- | --- | --- |
| riskLevel | string | "low" ¦ "medium" ¦ "high" ¦ "critical" |
| categories | string[] | e.g. ["email", "api_key", "financial"] |
| matches | Match[] | Array of {type, value, start, end} |
| summary | string | Human-readable: "email address and API key detected" |

## 2.2  Detection Categories & Methods

| Task | Details | Output |
| --- | --- | --- |
| Emails | Regex: RFC-5321 compliant email pattern Flag: medium risk | Medium |
| Phone Numbers | Regex: US/international formats Flag: medium risk | Medium |
| Physical Addresses | Keyword + pattern: street/ave/blvd + zip Context-sensitive | Medium |
| Credit Card Numbers | Regex: 13–16 digit, major card patterns Luhn algorithm check to reduce false positives | Critical |
| SSNs | Regex: XXX-XX-XXXX format Exclude obviously fake (000, 666) — Critical | Critical |
| API Keys / Tokens | High-entropy string detection (Shannon entropy > 4.0) Common prefixes: sk-, ghp_, AKIA, xoxb-, Bearer Min length: 20 chars — Critical | Critical |
| Passwords | Keyword proximity: 'password:', 'pwd=', '"password":' High-entropy strings after assignment operators — Critical | Critical |
| Health Information | Medical keywords: patient, diagnosis, prescription, ICD, DOB, MRN HIPAA-adjacent terms — High | High |
| Financial Data | Keywords: invoice, revenue, EBITDA, bank account, routing number Currency patterns — High | High |
| Legal Language | Keywords: confidential, attorney-client, privileged, NDA, without prejudice Counts threshold — High | High |
| Source Code | Detect code blocks via backticks or indented patterns Language keywords: import, function, class, const, var, def — Medium/High | Medium |
| Internal URLs | Detect private IP ranges: 10.x, 192.168.x, 172.16–31.x Intranet TLDs: .internal, .local, .corp — High | High |
| Business Terms | Configurable keyword list: roadmap, acquisition, merger, layoff User-customizable — Medium | Medium |
| Customer Data | Patterns: account #, customer ID, order #, ticket # Combined with names — High | High |

## 2.3  Risk Level Mapping

- Low — Nothing detected. Safe to submit.

- Medium — Possible personal info, business terms, or source code. User discretion advised.

- High — Clear sensitive data: customer info, health, legal, financial, internal URLs.

- Critical — Credentials, SSNs, credit cards, API keys, tokens. Always interrupt.

The overall risk level is the maximum of all individual category risks.

## 2.4  Sensitivity Modes

Users choose a sensitivity mode during onboarding (and can change in settings):

- Basic — Only Critical detections generate warnings.

- Balanced (default) — Medium and above generate warnings.

- Strict — All detections (Low+) show the risk badge; Medium+ interrupt.

## 2.5  Performance Requirements

- Scanning must complete in under 50ms for typical inputs (< 4,000 characters).

- Debounce scans by 300ms on input events to avoid scanning every keystroke.

- For very large pastes (> 10,000 chars), run scan asynchronously and update badge after.

- Never block the browser's main thread.

## 2.6  Test the Detector (Unit Tests)

Before wiring the detector to the UI, write unit tests using Jest or Node's built-in test runner:

- Test each regex with known-good and known-bad inputs

- Test entropy checker with real API keys and normal words

- Test risk level aggregation (highest category wins)

- Verify no false positives on common innocent text

PHASE 3: Content Scripts & UI Duration: 1.5–2 weeks • Risk badge, warning modal, redaction, per-site DOM hooks

## 3.1  Site Adapters (Per-Site DOM Selectors)

Each supported AI site uses a different DOM structure. Create one adapter file per site in src/content/sites/. Each adapter exports:

- getInputElement() — returns the active text input/textarea/contenteditable

- getSubmitButton() — returns the send/submit button

- getBadgeAnchor() — returns the element near which to inject the risk badge

Use MutationObserver in the main content script to detect when these elements appear (AI sites are SPAs and load dynamically).

| Site | Input Selector Hint | Submit Selector Hint |
| --- | --- | --- |
| ChatGPT | #prompt-textarea or div[contenteditable] | button[data-testid='send-button'] |
| Claude.ai | div[contenteditable='true'] | button[aria-label='Send message'] |
| Gemini | div[contenteditable='true'].ql-editor | button.send-button or mat-icon-button |
| Perplexity | textarea[placeholder] | button[aria-label='Submit'] |
| Copilot | textarea or div[contenteditable] | button[type='submit'] |

Caution: Selectors Break Often AI sites update their UIs frequently. Design the adapter pattern so you only need to change one file per site when selectors break. Add a fallback: if the preferred selector fails, try a list of backup selectors. Log a clear warning to the console when none are found.

## 3.2  Content Script Main Loop

In src/content/content.js, on page load:

- Use MutationObserver to watch for the input element to appear.

- Once found, attach an input event listener (debounced 300ms).

- On each input event, call detector.scan(inputText).

- Update the risk badge based on the result.

- Intercept the submit button click via a capture-phase event listener.

- If risk >= threshold (based on user sensitivity), call showWarningModal(result).

- In the modal: handle Redact, Rewrite, Submit Anyway, and Cancel actions.

## 3.3  Risk Badge (Inline Indicator)

The badge is a small, non-intrusive element injected near the AI input box.

- Inject a <div id='asg-badge'> just outside the input area

- Style it with your own CSS (scoped with asg- prefix to avoid conflicts)

- Update its text and color class on every scan result:

  - asg-low → green dot + "Safe"

  - asg-medium → yellow dot + "Medium risk"

  - asg-high → orange dot + "High risk"

  - asg-critical → red dot + "Critical risk"

- Use position: absolute or inject it relative to the input wrapper

- On empty input, hide the badge

## 3.4  Warning Modal

When the user clicks Submit and the risk level meets the threshold, intercept the click (e.preventDefault()) and show the modal.

The modal is a full-screen overlay with a centered card. It must:

- Show a plain-English description of what was found (from detector result.summary)

- List detected categories without jargon (e.g. "email address", "possible API key")

- Offer 4 action buttons in order of safety:

  - Redact automatically — replace sensitive values with [EMAIL REDACTED] etc.

  - Rewrite safely — call optional cloud API to rewrite (with consent prompt if first use)

  - Submit anyway — close modal, let original submission proceed

  - Cancel — close modal, return user to editing

- Be closeable with Escape key

- Not store or transmit any text

UX Principle: Helpful, Not Punitive The modal must never feel like a blocking error or accusation. Use friendly, plain language. "This message may contain private information" not "SECURITY VIOLATION DETECTED." Always give the user an easy out — Submit anyway must always be available.

## 3.5  Redaction

When the user clicks Redact automatically, replace all detected match values in the input with their placeholder:

- [EMAIL REDACTED] for email addresses

- [PHONE REDACTED] for phone numbers

- [CARD REDACTED] for credit card numbers

- [SSN REDACTED] for social security numbers

- [API_KEY REDACTED] for API keys and tokens

- [NAME REDACTED] for names in context

- [ADDRESS REDACTED] for physical addresses

- [CONFIDENTIAL] for legal/business terms

After redaction: re-run the scanner on the new text and re-evaluate risk. Update the input value in the DOM and dismiss the modal. The user can review and submit the redacted text.

## 3.6  Safe Rewrite (Optional Cloud Feature)

This is the only feature that sends text to an external server. Gate it with explicit user consent:

- On first use of Rewrite, show an additional consent prompt explaining that the text will be sent to an AI API for rewriting.

- If user agrees, make a POST request to the configured rewrite API endpoint.

- Send: { prompt: originalText, categories: detectedCategories, instruction: "Remove or generalize all sensitive details" }

- Display the rewritten prompt in a preview panel within the modal.

- User can accept the rewrite (replaces input) or go back.

Default: No Cloud Calls The rewrite API is off by default. Only enable it after explicit user consent. Store consent preference in chrome.storage. Make the API endpoint configurable in settings so privacy-conscious users can point it at a self-hosted model.

PHASE 4: Settings, Onboarding & Storage Duration: 1 week • User configuration, first-install flow, persistent preferences

## 4.1  Storage Schema

Use chrome.storage.local for all user preferences. Define the schema in src/shared/storage.js:

- enabled (boolean) — master on/off switch

- sensitivity (string) — "basic" | "balanced" | "strict"

- enabledSites (object) — { chatgpt: true, claude: true, gemini: true, ... }

- customDomains (string[]) — user-added AI site domains

- disabledCategories (string[]) — categories the user has muted

- allowRewrite (boolean) — user consented to cloud rewrite

- rewriteApiEndpoint (string) — optional custom endpoint

- analyticsEnabled (boolean) — default true, user can opt out

- onboardingComplete (boolean) — tracks first-install flow

## 4.2  Onboarding Page

Open the onboarding page automatically on first install via the chrome.runtime.onInstalled event in the service worker. The page lives at src/onboarding/onboarding.html.

Onboarding has 3 steps:

- Step 1 — What AI Safety Guard does — Short explanation with icons. Emphasize: scans locally, nothing stored, you're in control.

- Step 2 — Choose your sensitivity — Three clearly explained options: Basic, Balanced, Strict. Default to Balanced.

- Step 3 — Choose supported sites — Checkboxes for each AI site. All enabled by default. Option to add a custom domain.

End with a Get Started button that saves settings and closes the page.

## 4.3  Settings Popup

The popup (clicking the extension icon) shows a compact settings panel:

- Master toggle — enable / disable the extension

- Sensitivity selector — Basic / Balanced / Strict

- Site toggles — per-site enable/disable

- Add custom domain field

- Link to full settings page (optional) for advanced config

- Version number and link to privacy policy at the bottom

All changes save immediately to chrome.storage and take effect on the next input scan. No Save button needed.

## 4.4  Message Passing

Content scripts cannot directly access chrome.storage in all cases. Set up a simple message-passing pattern via the service worker:

- On startup, content script sends GET_SETTINGS to the service worker

- Service worker responds with the current settings object

- When settings change in the popup, service worker broadcasts SETTINGS_UPDATED to all active content scripts

- Content scripts update their local copy and re-evaluate risk if text is present

PHASE 5: Testing, Privacy Audit & Chrome Web Store Submission Duration: 1–1.5 weeks • Ship with confidence

## 5.1  Manual Testing Checklist

| Task | Details | Output |
| --- | --- | --- |
| Basic Detection | Paste an email → badge shows Medium Paste an API key → badge shows Critical Paste normal text → badge shows Low/hidden | Pass/Fail |
| Submit Interception | Click send with high-risk text → modal appears Click Submit anyway → submission proceeds Click Cancel → modal closes, text intact | Pass/Fail |
| Redaction | Click Redact → sensitive values replaced with placeholders Re-scan after redaction → lower risk level Redacted text can be submitted normally | Pass/Fail |
| Per-Site Testing | Test on ChatGPT, Claude, Gemini, Perplexity, Copilot Verify badge appears near input on each site Verify submit interception works on each | Pass/Fail |
| Settings | Change sensitivity → badge updates on next input Disable a site → no badge or interception on that site Add custom domain → extension activates on it | Pass/Fail |
| Onboarding | Fresh install → onboarding page opens All 3 steps work, sensitivity choice is saved Revisiting onboarding page works correctly | Pass/Fail |
| Edge Cases | Empty input → no badge Very long input (10k+ chars) → no UI freeze SPA navigation (new chat) → content script still works | Pass/Fail |

## 5.2  Privacy Audit

Before submitting to the Chrome Web Store, conduct a formal privacy review:

- Verify no prompt text is sent to any server during normal scanning

- Audit all network requests using Chrome DevTools Network tab

- Confirm analytics events contain zero prompt content

- Review chrome.storage contents — should only contain settings, never prompt text

- Test the rewrite flow — verify text is ONLY sent when user explicitly clicks Rewrite and consents

- Review the Privacy Policy (required by CWS) — document exactly what is collected

## 5.3  Performance Testing

- Time the detector on inputs of 100, 1,000, 5,000, and 10,000 characters

- Confirm no jank or input delay on any of the 5 supported sites

- Verify the extension adds less than 20ms latency to input events

- Run the extension alongside heavy pages (ChatGPT with long conversations)

## 5.4  Chrome Web Store Submission

- Create a CWS developer account — One-time $5 fee at chrome.google.com/webstore/devconsole

- Prepare the store listing — Extension name, short description (132 chars), detailed description, screenshots (1280x800 or 640x400), promotional tile, and category (Productivity)

- Prepare the privacy disclosures — Justify all permissions in the CWS form. For host_permissions, explain why each AI site is needed. Declare all remote code — there should be none in MVP.

- Package the extension — Run npm run build, then zip the dist/ folder (not the root)

- Submit for review — CWS review typically takes 1–3 business days for new extensions. Prepare for possible requests for clarification on permissions.

CWS Review Tips The most common rejection reason is overly-broad permissions. Only request host_permissions for the exact supported AI site URLs — not <all_urls>. Clearly justify "scripting" and "storage" permissions in the submission form. Include a test account or demo instructions if the reviewer needs to see the extension in action.

# Appendix: Analytics (Privacy-Safe)

Use a lightweight, cookieless analytics solution (e.g., Plausible, Umami, or a custom endpoint). Track only aggregated, non-identifying events:

- extension_installed

- warning_shown (with risk_level only, no prompt content)

- redaction_completed

- rewrite_requested

- submit_anyway_clicked

- onboarding_completed (with sensitivity_chosen)

Never Include Prompt Content in Analytics Event payloads must never contain any portion of the user's input text, detected values, or site-specific identifiers that could be traced back to a person. Only include aggregate signal: risk level, action taken, and extension version.

# Appendix: Future Roadmap

These features are explicitly out of scope for MVP but should inform architecture decisions now:

- File upload scanning — detect sensitive content before attaching files to AI tools

- Local AI classifier — replace regex-only detection with an on-device ML model (e.g., ONNX)

- Firefox and Edge support — abstracted browser API layer makes this straightforward

- Team policies — enterprise admin console to push detection rules to employees

- Weekly personal AI safety report — summary of what you almost sent

- AI tool safety score overlay — rate each AI tool's data handling practices

# Appendix: Key Development Gotchas

- MV3 service workers are ephemeral — they shut down when idle. Never rely on in-memory state in the service worker. Read from chrome.storage on each message.

- ContentEditable inputs — ChatGPT and Claude use div[contenteditable] not textarea. Read innerText, not value. Write back by setting innerText and dispatching an input event.

- CSP on AI sites — some AI sites have strict Content Security Policies. Inject styles via a <style> tag inside your shadow DOM or use the extension's CSS injection (chrome.scripting.insertCSS) to avoid CSP violations.

- SPA navigation — AI tools are single-page apps. A new conversation doesn't reload the page. Use MutationObserver on document.body to detect when the input is replaced and re-attach your listeners.

- Shadow DOM — some sites use Shadow DOM internally. Your querySelector calls won't pierce it. Use document.querySelector first, then if needed, traverse into shadowRoot manually.

- Event capture phase — to intercept form submissions reliably, attach your click listener in the capture phase: button.addEventListener('click', handler, true). Bubble-phase listeners may fire after the site's own listener has already sent the request.